## WIP
Sl. No | Brand Name | Country | Geo Tag | CR Description | Estimated CR Value (INR) | CSM Acc Mgr | Project Manager | SoW Sign Date | Committed Date of Delivery | Current Status | ETA for Delivery | BRD Link | SOW Link
1 | BBW | Indonesia | SEA | Postal code Address changes | N/A | Nitika | Ramraj Singh | Ramraj Singh | Nitika | Go live | 2022-06-08 |  | Nitika
2 | BBW | MY | SEA | Qwikcilver | N/A | Nitika | Ramraj Singh | Ramraj Singh | Nitika | UAT | 2022-06-15 |  | Nitika
3 | BBW | HK | SEA | OMS Integration |  | Nitika | Ramraj Singh | Ramraj Singh | Nitika | UAT | Ramraj Singh |  | Nitika
4 | BBW | TH | SEA | Pace for Thailand | N/A | Sneha | Ramraj Singh | Ramraj Singh | Sneha |  | Ramraj Singh |  | Sneha
5 | BBW | AU | SEA | Rewards - Multiple Loyalty Program | Nitika | Nitika | Ramraj Singh | Ramraj Singh | Nitika |  | Ramraj Singh |  | Nitika
6 | BBW | AU | SEA | Rewards - Issue with Voucher Code Based cart promotion Buy X Get Y | Nitika | Nitika | Ramraj Singh | Ramraj Singh | Nitika |  | Ramraj Singh |  | Nitika
7 | Asics SEA | PH | SEA | Ordazzle Integration Development | Was part of initial SOW | Nitika | Vindhya | N/A | Nitika | Solutioning | Vindhya | https://drive.google.com/drive/folders/1wlOW1_hrH-rACRCgFlqhBv_THULMemrb | Nitika
8 | Asics SEA | SG, MY, TH | SEA | One Asics End point V2 migration | 4,23,372.51 | Sneha | TBD |  | Sneha |  |  | https://drive.google.com/drive/folders/137piXUppzWN5Ful4b7igSBNHfBP8Zqfg | Sneha
9 | Asics SEA | SG, MY, TH | SEA | UX/UI rewamp | 8,32,353.28 INR | Sneha | Avinash | NA | Sneha |  | TBD | https://drive.google.com/drive/folders/1s9nCvpcbmnW__Zd38EcoYxvXzP-HH5k7 | Sneha
10 | Asics SEA | SG, MY, TH | SEA | AAP order data integration | N/A | Sneha | Suparna | NA | Sneha | Fixed | Suparna |  | Sneha
11 | Asics SEA | SG, MY, TH | SEA | 3DS 2.0 Implementation | Sneha | Sneha | TBD |  | 2022-09-01 |  |  | https://drive.google.com/drive/folders/15EwBoxf03iGsQDkeKygTlIgUhCjoTXHL | Sneha
12 | Asics SEA | SG, MY and TH | SEA | Line level cancellation details flow to Netsuite changes in Integration | Sneha | Sneha | TBD |  | Sneha | Solutioning |  |  | Sneha
13 | Levis PH | PH | SEA | capillary-etaily-Integration | Sneha | Sneha | Vindhya | Vindhya | Sneha | Dev | Vindhya |  | Sneha
14 | Levis PH | PH | SEA | CRM Implementation |  | Raghava | Raghava | Raghava | Raghava |  | Raghava |  | Raghava
15 | Biba | India | India | AED Currency enablement | Kanishk | Kanishk | Ramraj Singh | Ramraj Singh | Kanishk | UAT | 6th June |  | Kanishk
16 | Biba | India | India | Gift Voucher - Cequity Integration | Kanishk | Kanishk | Ramraj Singh | Ramraj Singh | Kanishk | UAT | Ramraj Singh |  | Kanishk
17 | Biba | India | India | Razorpay Integration | Kanishk | Kanishk | Ramraj Singh | Ramraj Singh | Kanishk |  | Ramraj Singh |  | Kanishk
18 | Biba | India | India | Pivot Roots 1- Order line Sales report | Kanishk | Kanishk | Ramraj Singh | Ramraj Singh | Kanishk |  | Ramraj Singh |  | Kanishk
19 | Spar | India | India | CR for Mobile based OTP sign up & sign in | Venkat | Venkat |  | Venkat | Venkat |  |  |  | Venkat
20

## account ownership
Pramod | CSM
Venkat |  | landmark | spar | shwapno | namdhari | hypermarket acnt
Richard |  | joy alukas | prestige ttk | medsmart | shimano | Asics ind | Onitsuka Tiger India
kanishk |  | biba
Nikita M | CSM | Asics SG, MY,TH | Asics PH | Max | Babyshop | Kanmo | Levis | BBW
Sneha | Associate Manager | Asics SG, MY,TH | Asics PH | Max | Babyshop | Kanmo | Levis | BBW
Avinash | Delivery Manager | Asics SG, MY,TH | Asics PH | Max | Babyshop | Kanmo | BBW
Chun | Delivery Manager | Levis
Nitika S | CSM
Sadiq | DM | EMEA | matalon | redtag | ajalan | Apex Bangladesh
Sachin kampawar | DM | EMEA | americana | herfy | Little ceasar
Note on E12: 14 requests. Sadiq to confirm on 7 jun -Suparna Mallik
Note on G12: 3 requests received -Suparna Mallik